## Sheet1
Modules | Total Estimated Hours Needed | Operations Group | HR Group | AWBC Group | Payroll Group | Finance | BAM Configure Group & IT | Estimated Completion | Notes
BAM IT Implementations | 229 | 8 | 23 | 0 | 6 | 2 | 212
Thomas and Co - Ready for testing, Wesley to schedule internal review meeting with team to validate data. | 12 | 0 | 1 | 0 | 1 | 0 | 10
Award Co - Ready for testing, Wesley to schedule internal review meeting with team to validate data. | 11 | 1 | 0 | 0 | 0 | 0 | 10
Walton - Ready for testing, Wesley to schedule internal review meeting with team to validate data. | 11 | 0 | 1 | 0 | 0 | 0 | 10
Dayforce New Hire Feed - Discovery to be scheduled next week. | 25 | 0 | 5 | 0 | 0 | 0 | 20
Celerant POS - Ready for testing, Wesley to schedule internal review meeting with team to validate data. | 11 | 1 | 0 | 0 | 0 | 0 | 10
External Job Boards - Discovery needed | 25 | 0 | 5 | 0 | 0 | 0 | 20
WOTC IFRAME - to be placed into preboarding per Vida 2/9/2023 | 3 | 0 | 1 | 0 | 0 | 0 | 2
MHC - Second discovery session to be scheduled with Jim and team. | 15 | 0 |  | 0 | 5 | 0 | 10
Optimed - Discovery Needed | 25 | 0 | 5 | 0 | 0 | 0 | 20
MedCOM - Discovery Needed | 25 | 0 | 5 | 0 | 0 | 0 | 20
Finance Portal - Second discovery session/process decission meeting scheduled for 2/15/2023. Then development estimates will be needed. | 66 | 6 | 0 | 0 | 0 | 0 | 60
Concur - Initial file has been built, Wes to validate it meets specs, then schedule data review internal session and system testing. | 22 | 0 | 0 | 0 | 0 | 2 | 20